## Risks
Risk ID | Date Risk Raised | Raised by | Affected Asset | Risk Owner | Risk Statement | Risk Likelihood | Risk Consequence | Risk Rating | Current Risk Comments | Control areas for existing controls | Risk Treatment Decision | Risk Treatment Plan | Control areas for new treatment measures | Treated Residual Risk Likelihood | Treated Residual Risk Consequence | Treated Residual Risk | Date of Risk Owner's Acceptance /Treament Approval | Date Risk Treatment due | Date Risk Treatment Implemented
101 |  | David Simpson | Personnel Files | HR Manager | Personnel information may be inadvertently or deliberately exposed | C (Possible) | 3 (Moderate) | High | Files are physically secured but there are poor handling practices | A.13.2.4 A.11.1.2 A.11.1.3 | Mitigate | Provide awareness training for all staff regarding information classification and handling | A.7.2.1 A.8.2.2 A.8.2.3 | E (Rare) | 3 (Moderate) | Low

## Field Descriptors
Fields in the "Risk Register" worksheet should be filled in as per following definitions and guidelines
Field Name | Definition / Instructions
Risk ID | Running serial number. Number should be assigned sequentially every time a new risk is identified.
Location | Physical location of the risk
Date Risk Raised | Date risk raised
Raised by | Person raising the risk
Affected Asset | Name / category of the asset related to the risk
Risk Owner | The owner of the risk
Key Factors | Key factor (a few words) to highlight the context
Threat | Brief description of an unwanted (deliberate or accidental) event that may result in harm to an asset.
Vulnerability | Brief description of a weakness that could cause the threat
Risk Statement | Statement of the potential risk
Current Risk Likelihood | Probability or likelihood of existing occurring considering existing controls in place. Use drop down boxes and refer to Risk Criteria sheet
Current Risk Consequence | Consequence or impact of existing risk without new treatment measures, if the risk eventuates. Use drop down boxes and refer to Risk Criteria sheet
Current Inherent Risk | Rating or exposure of untreated risk considering existing controls in place, but without new treatment measures, if the risk eventuates. Refer to "Risk Criteria" worksheet for possible values and definitions.
Current Risk Comments | Comments / remarks to qualify / explain existing controls in place. Also comments to explain / qualify any recommendations for risk acceptance
Controls areas for existing controls | List of control numbers from the standard ISO27001 Annex A that correspond to the existing controls in place
Risk Treatment Recommendation | Possible values are "Mitigate", "Accept" Mitigate = recommendation is to mitigate the risk. new treatment measures being proposed / applied Accept = recommendation is to accept the risk without any new treatment measure
Risk Treatment Plan | Comments / remarks to qualify / explain new treatment measures being proposed / applied
Control area for new treatment measures | List of the relevant control area from the standard ISO27001 Annex A that correspond to the new treatment measures proposed / applied
Treated Residual Risk Likelihood | Probability or likelihood of treated risk occurring assuming the recommended treatment measures have been applied. Possible values A to E. Refer to "Risk Category" worksheet for definition. To be left blank if the Risk Treatment Recommendation is "Accept Risk"
Treated Residual Risk Consequence | Consequence or impact of treated risk assuming the recommended treatment measures have been applied. Possible values 1 to 5. Refer to "Risk Category" worksheet for definition. To be left blank if the Risk Treatment Recommendation is "Accept Risk"
Treated Residual Risk | Rating or exposure of treated residual risk considering the treatment measure(s) has been applied, if the risk eventuates. Refer to "Risk Category" worksheet for possible values and definitions.
Date of Risk Owners Acceptance/Treatment Approval | Date when the Risk Owner accepted the risk or approved the treatment plan
Risk Treatment Owner | Person accountable for implementing the treatment plan
Date Risk Treatment due | Planned implementation date of risk treatment plan / new control, or Leave blank or N/A if Risk Treatment Recommendation is "Accept Risk"
Date Risk Treatment implemented | Actual implementation date of risk treatment plan / new control, or Leave blank or N/A if Risk Treatment Recommendation is "Accept Risk"
Date of Review and Nature of Updates | Add a column with the date of the review of the risk and any changes that were made to any component of the risk

## Risk Criteria
The table below forms the basis for risk assessment for the Amcom ISMS in conjunction with the Amcom Risk Management Policy
Current / Treated Risk Matrix
Level of Probability | Level of Consequence
| 1 | 2 | 3 | 4 | 5
A (Almost Certain) | Medium | High | Very High | Critical | Critical
B (Probable) | Medium | High | Very High | Critical | Critical
C (Possible) | Low | Medium | High | Very High | Very High
D (Improbable) | Low | Low | Medium | High | High
E (Rare) | Low | Low | Low | Medium | Medium
| 1 (Insignificant) | 2 (Minor) | 3 (Moderate) | 4 (Major) | 5 (Catastrophic)